## Sheet1
2023 STATE BUSINESS ENABLING REFORMS ACTION PLAN | [10 empty] | PROGRESS REPORT
S/N | BUSINESS ENABLING REFORM AREAS | REFORM OBJECTIVES | ACTION STEPS | DESCRIPTION AND KEY TARGETS | BENEFICIARIES | RESPONSIBLE MDA | CONTRIBUTING MDAS | EST. COST | PLANNED START DATE | PLANNED END DATE | STATUS | DESCRIPTION OF STATUS | NEXT STEPS
1 | Improved Firm Access to Reliable Electricity | (i) To develop a framework to identify existing up-grid demand clusters (ii) To create a platform for customer’s complaint and submission | (i) Conduct stakeholders’ engagement and allocation process. | Our target is to strengthening the existing mini-grid power supply to areas not covered by the national grid so as to achieve at least 50% coverage by the end of 2023. To resolve at least 100 complaints on issues relating to electricity. | Industrialist, MSMEs, Operators. | Ministry of Energy and Mineral Resources | * Ondo State Electricity Board (OSEB) * Ondo State Electricity Regulatory Bureau (OSERB) * Ondo State Power Company (OSPC) * Office of Public Utility (OPU) | N28m | 1st Feb, 2023 | 20th Dec, 2023 | Completed Impact: We have bridged the electricity gap in the State and reduced the energy poverty and inequality by 45% | The State held a stakeholder engagement & workshop on Sept. 14th, 2023 , Oct. 3rd 2023 and Nov. 23rd, 2023 with maximum demand customers and representatives of the Nigeria Electricity Regulatory Commission(NERC)Transmission Company of Nigeria, (TCN) Benin Electricity Distribution Company (BEDC), Electricity Vendors, Providers e.t.c in attendance. Also, the ministry was able to map out thirty (30) underserved and served commmunities in the states. | This activity is a continous project which will continue in 2024 as more investors have shown interest in connecting more communities
|  |  | (ii) Carryout site possession processing with the service providers to enables proper investigation and site layout. | [7 empty] | Completed Impact: i) Citizens are better informed to exercise their rights to electiricty ii) created mutual understanding and awareness between BEDC and the citizens
|  |  | (iii) Execute Memorandum of Understanding stating the regulatory procedures, parameters and billing | [7 empty] | Completed Impact: i) it increases investors confidence and trust in the state government ii) it outlines clear procedures and timelines, simplying the investment processes iii) Creation of job, both direct and indirect contribution to economic growth iv) It provides a level of guarantee and assuranve,reducing the risk for investors | The state signed three (3) Memoradium of Understanding (MOU) with investors and issued licences to two (2) other service providers | Three(3) additional Memorandia of Understanding (MOUs) are currently in the pipeline and are expected to be signed in year 2024
|  |  | (iv) To create a complaint desk within the Ministry of Energy. | [7 empty] | Completed Impact: Over one hundred (100) complaints were addressed and resolved. | A functional complaint desk has been created within the Ministry of Energy premises. A qualified personnel has been deployed to serve as a customer service agent. A dedicated telephone line (08070966100/07083258600) has been provided for the purpose of receiving complaints between the hours of 8.00am to 4.00pm on monday to friday except on puiblic holiday. | it a continuous process
2 | Increase Fibre Optic Network Deployment Access to Broadband | (i) To increase internet broadband penetration and explore the potential internet usage. | (i) Carryout constant and effective monitoring with Odua Infraco Resources Limited for proper installation of fiber optics | (i) Ensure that the state’s infrastructure growth is sustained and inclusive (ii) Protection of prospective local and foreign investors (iii) To maintain the N145 per linear meter fee charged for broadband deployment | * Government institutions and parastatals * The organized private sectors * Technology Hubs and investors | Ondo State Information Technology Agency (SITA) | * Ministry of Infrastructure, Lands and Housing * Ministry of Physical Planning and Urban Development * Performance and Project Implementation Monitory Unit (PPIMU) | - | 3rd Jan., 2023 | 31st Dec., 2023 | Completed Impact: 390 kilometers of Fibre optic cables were laid across the state with a view to sustaining the infrastructural growth in internet broadbrand | Ondua Infraco Resource Limited was contracted to install the cables | The project will continue in 2024 as more area will be covered with internet broadband
|  |  | (ii) Draw up competitive right of way investment framework for potentials broadband off-takers. | [5 empty] | 8th Feb., 2023 | 9th Oct., 2023 | Completed Impact: a well developed framework streamlining the ROW processes and charges in place to encourage potential investors | A detailed Framework on RoW was developed and publicised on the Agency's website showing the processes and incentives available to potential broadband off-takers | Not Applicable
3 | Increase Transparency of official fees and procedures | (i) To be transparent and make public all fees, service delivery timeline and cost of all key business enabling environment state level MDAs. | (i) Review the Ondo State Revenue Administration Law of 2018 to accommodate new fees and rates where and if necessary | (i) To ensure that the citizenry and public are aware of all government taxes and rate | The citizenry Business owners | Ondo State Internal Revenue Services | * Ministry of Commerce, Industry and Cooperative Services * Ministry of Environment * Ministry of Transport * Ondo State Signage and Advertisement Agency * Ministry of Lands |  | 10th Jan., 2023 | 31st June., 2023 | Completed Impact: Citizens are aware of the accurate fees to pay per transaction | The ODIRS has a functional and interractive website where all fess and levies are displayed. Also, the revenue administration law has fess and levies incorporated | N/A
|  | (ii). To create a one stop for Information sharing, grievances and redress mechanism within ODIRS on fees related issues. | (ii) Ensure that the Revenue Administration Law which contains all approved rates and fees is published and maintained on the Ondo State Government website as well as the website of the Ondo State Internal Revenue Services and key business enabling MDAs. | (ii) To ensure that all complaints are resolved within 72 hours; and where the complaint cannot be resolved within the 72 hours, the complainant must be notified of the efforts made to resolve the complaints. |  |  |  |  | 6th March, 2023 | 6th April, 2023 | Completed Over 80% of complaints received are resolved within 48 hours and pending matters are escalated to the appropriate desks while the taxpayer is kept abreast of the resolution status. | The contact center addresses complaints from across the state and beyond using mediums like phone calls via (08188397000/09028477004/08104864804) and emails via (info@odirs.ng/contactus@odirs.ng). | Not Applicable
|  |  | (iii) Publish the procedures and timeline for service delivery for 5 key business enabling MDAs (Business Premises Permit by Ministry of Commerce and Industry, EIA by Ministry of Environment, Signage permit by Ondo State Signage Agency, Vehicle Inspection Certificate by Ministry of Transport and Survey Plan by Ministry of Lands. | (iii) To blocked loopholes for diversion of government revenue. |  |  |  |  | 31st Dec, 2022 | 31st Dec, 2023 | Completed Impact: 1 Removes beaurucratic bottlenecks 2. Create efficiency in tax administration | Following the Executive Order, the procedure, processes and timelines of 5 key business enabling MDA`s has been uploaded on government website with URL: https://ondostate.gov.ng/index.php/land-reg/ | Not Applicable
|  |  | (iv) Continue with public awareness program on TV, Radio and other new media on the available electronic platform for payment of all government revenue. | [5 empty] | 31st Dec, 2022 | 31st Dec, 2023 | Completed Impact: 1. Citizens are aware of the various tax components 2. Easy and transparent payment options | Public awareness has been consistent on radio stations via Adaba FM (88.9), Alalaye FM (96.5) Orange FM (94.5) and television station via OSRC. | Continue to create public awareness
4 | Increased Sustainable Large-scale Investment and Development of an Effective PPP Framework for the State | (i) To attract investment into Ondo State and Promote after care services for the sustainability of existing investment / industries in the State (ii) To have a transparent and effective Public Private Partnership engagement process and procedures for efficient private sector collaboration | (i) Development and Publication of Ondo State Industrial guide and Ondo State Investment guide and other investment promotion fliers | * To establish at least for (4) large scale industries in the State by the end of year 2023. * To showcase the investment potential of the state to the outside world with a view to industrializes the State. * To understand how Lagos, Kaduna and Edo State implement and execute their PPP framework. | * The State government * The Private sector | Ondo State Development and Investment Promotion Agency (ONDIPA) | Ministry of Commerce, Industry and Cooperatives * Performance and Project Implementation Monitoring Units (PPIMU) | 40m | 16th Feb., 2023 | 2nd March, 2023 | Completed Impact: Three (3) out of the four (4) proposed industry have been established and one thousand two hundred and four (1204) direct jobs have been created. | Investment guide and flyers already published on the Agency's website | Not Applicable
|  |  | (ii) Develop a Strategic framework to drive investment in the State | [5 empty] | 4th Jan, 2023 | 25th Jan, 2023 | Completed Impact: The areas where the state has comparative and competitive advantage in terms of investment are being developed. | A 10-year investment strategic document has been published on the Agency's website | Awareness campaign for investors to take informed decision on investment opportunities in Ondo State
|  |  | (iii) Organize at least four (4) investment summit in year 2023 i.e (2 in Nigeria and 2 International) | [5 empty] | 13th March, 2023 | 20th September, 2023 | Ongoing Challenges: Unavailabilty of funds to organize the summit and conference | Investment Summit organized in the US and Investment conference organized in Lagos | To organize investment summit in United Kingdom and Abuja Nigeria subject to the availability of funds
|  |  | (iv) Carry out study tour to Kaduna, Lagos and Edo State (v) Engage the Legal drafting Department of Ministry of Justice to draft the PPP framework/Law (vi) Conduct Public hearing on the PPP Bill (vii) Liaise with the House of Assembly to ensure the passage of the bill. | [5 empty] | 10th April, 2023 | 10th October, 2023 | Completed Impact Strengthened the organized private sector in the State Completed | The state embarked on a study tour to Lagos, Kaduna and Edo state in collaboration with the organized private sector. | Not Applicable
5 | Development of Transparent Land Titling and Registration System in Ondo State | (i) To achieve a fast and transparent open process in land titling and registration | (i) Conduct awareness and enlightenment campaign on the ease of access to land titling and Registration (ii) Meeting with stakeholders on Land management (iii) Follow up on the on-going Home Ownership Chartered of Ondo State Scheme (HOCOS) | (i) Land titling and Registration to be achieved within 60 days (ii) To maintain and sustain the process of land titling from manual to digital system | Land owner and investors | Ministry of Land and Housing | Ministry of Physical Planning and Urban Development Office of the surveyor General Ondo State Internal Revenue Services | N10.5m | 22nd Feb., 2023 | 15th Dec., 2023 | Completed Impact: 1. Ease of conducting property search 2. increase in application for title documents | 1. Organizations of road shows, community/stakeholders meetings 2. Organization of TV and Radios interviews witrh key officers involved in property titling 3. Establishment of efficient contact centers within the ministry | Not Applicable
6 | Increase Trans-border Trade between Neighbouring States particularly Agric Product | To regulate and promote trans-border trades between Ondo State and Boarder States | Compile list of Agro commodities / forestry products on a trusted online marketplace and standard levies for the products; | * Increase in volume of Agro-commodities / forestry products/trades in the State by 25% * To remove illegal levies collectors on the borderlines in the State in respect of Agro products | Ministry of Agriculture and Forestry | ODIRS, State Security Network (Amotekun) Office of the Surveyor General | 12m |  | 6th Feb., 2023 | 15th December, 2023 | Completd. IMPACT: The volume of Agro commodities trade in the State has incresead by 30%. This has also increased the revenue generated on agro commodities sales from 10 million naira in 2022 to about 26.8 million naira in 2023 | The Ministry of Commerce and Industry worked in collaboration with the Ministry of Agriculture and Forest Resources and consultants were also engaged to compile the list based on the State's economic advantage. The State also granted incentives to forest operators that voluntarily registered their operations in the State. | Not Applicable
|  |  | * Establishment of toll line and State taskforce to monitor and enforce compliance | [7 empty] | Completed. IMPACT: No more multiplicity of collection of fees at the boarder line of the state with the neighbouring states | The state government recruited personnel on contract basis to man the border post. Indentity cards were issued to the engaged personnel for the purpose identification and ward off miscreants | Not Applicable
|  |  | * Study tour to Oyo, Kwara and Ebonyi States to under-study their trans-border policy on Agro-logistic movements and border trades. | [7 empty] | Completed. IMPACT: The State was able to get a templates used in the design of its program in respect of the trans boarder trade particularly for Oyo State. |  | Not Applicable
7 | Quick Determination of Commercial Dispute | To establish a Special Court (e.g. Small Claims Court) for Commercial dispute of Micro and Small Enterprises. | Constitute a five-man technical committee for the establishment of the Small Claim Courts. - Conduct training for Magistrates and Registrars for the scheme - Conduct awareness campaign to sensitize the public on the existence of the Small Claim Court. - Employment of more Adjudicators such as Magistrates. | To ensure quick settlement of dispute and judgement delivered within 60 days To established at least (2) Small Claim Court in the State in year 2023 To maintain speedy and accelerated hearing | Medium and Small Scale Industrialist | Ondo State Judiciary | Ministry of Justice, Ministry of Finance | 50m | 13th Feb., 2023 | 10th Dec., 2023 | NO ACTIVITY: The State Judiciary not prepared to carry out the activities in 2023. | NO ACTIVITY | NO ACTIVITY