## Sheet1
ONDO STATE YEAR 2024 BUSINESS ENABLING REFORMS ACTION PLAN | [9 empty] | PROGRESS REPORT
S/N | BUSINESS ENABLING REFORM AREAS | REFORM OBJECTIVES | ACTION STEPS | DESCRIPTION AND KEY TARGETS | BENEFICIARIES | RESPONSIBLE MDA | CONTRIBUTING MDAS | PLANNED START DATE | PLANNED END DATE | STATUS | DESCRIPTION OF STATUS | NEXT STEPS
1 | I Improved efficiency in property registration and sustainability of the land based investment process | To achieve a fast and transparent open process in land titling and registration | (i) Utilize block chain technology to ensure the security and transparency of property records | Our target is to reduce the time taken to complete property registratio processes from the present 60 days to 40 days and implement mechanisms for expedient processing of documents, especially for time-sensitiv transactions. | Citizenry Landowners Property owners Investors | Ministry of Land, Housing and infrastructure | * Ministry of Physical Planning and Urban Development *Office of the surveyor General *Ondo State Internal Revenue Service | 10 Feb, 2024 | 20 July, 2024 | Completed Impact: We have reduced the time taking to complete property registration in Ondo state from the intial 60 days to 40 days. | The State Government intiated the Home Ownership Charter Scheme (HOCOS) aimed at ensuring that every resident of Ondo State who owns property has proper and genuine title documents to their properties. | Our next step is to further reduce the time taking to register property in Ondo State to 30 days.
|  |  | (ii) Establish a centralized and standardized database for property information accessible to all relevant government agencies. | [6 empty] | Completed Impact: Search can be conducted and information on property can be easily accessed using the searchable indexes such as name, gender, ownership type etc.
|  |  | (iii) Launch public awareness campaigns to educate citizens on the benefits | [6 empty] | Completed Impact: The Citizens are aware of the importance of the registration of title documents. This has lead to 20% increase in the application for registraion of totle documents. | Public awareness campaign has been consistent on radio and television station across the state such as Adaba F.M (88.9), Orange F.M (94.5), Alalaye F.M (96.5) and OSRC TV. | Continue the awareness comapign in other social media platforms.
|  |  | (iv) ) Review and update property laws and regulations to align with the digital transformation and promote sustainable land use. | [6 empty] | Not yet Implemented |  | The review of the property laws of Ondo State has commenced, and it is expected to be completed by the 4th quarter of 2025.
2 | Framework for private investment in Fiber Optic infrastructure | (i) broadband penetration and explore the potential internet usage | (i)review of existing regulations related to fiber optic infrastructure investment. | (i) infrastructure growth is sustained and inclusive (ii)Protection of prospective local and foreign investors (iii) To maintain the N145 per linear meter fee charged for broadband deployment | * Government institutions and parastatals * The organized private sectors * Technology Hubs and Investors | Ondo State Information Technology Agency (SITA) | * Ministry of Infrastructure, Lands and Housing * Ministry of Physical Planning and Urban Development * Performance and Project Implementation Monitory Unit (PPIMU) *Ondo State Ministry of Justice |  |  | Completed Impact: Per Linear meter of Fibre Optic cable has been capped at ₦145. | The regulation related to Fibre Optic Infrastructure Investment in Ondo State has been published. | Not Applicable
|  |  | (ii) Implement open access policies to encourage competition and allow multiple service providers to share the same fiber optic infrastructure. |  |  |  |  | 16th Apr, 2024 | 20th Oct, 2024 | Completed Impact: a well developed framework streamlining the ROW processes and charges in place to encourage potential investors | A detailed Framework on RoW was developed and publicised on the Agency's website showing the processes and incentives available to potential broadband off-takers | Not Applicable
3 | Development of an Effective PPP Framework | (i) To attract investment into Ondo State and Promote after care services for the sustainability of existing investment / industries in the State | (i) Assess and update existing laws and regulations related to PPPs to ensure they are clear, comprehensive, and conducive to private investment. | (i) The key target is to foster a transparent and robust regulatory environment. This includes clear legal frameworks, risk sharing mechanisms, and efficient dispute resolution mechanisms to attract private sector investment and ensure sustainable collaboration between public and private entities | * The State government * The Organized Private Sector | Ondo State Development and Investment Promotion Agency (ONDIPA | * Ministry of Commerce, Industry and Cooperatives * Performance and Project Implementation Monitoring Units (PPIMU) *Ministry of Finance *Ministry of Economic Planning and Budget. * Ministry of Justice | 10th Feb, 2024 | 30st Sept, 2024 | Complete Impact: 60% of Investors in the state particularly those on PPP project are aware and have access to the PPP regulations in the state. (ii) The PPP regulations and laws are available on the official webiste of Ondo state. | A dedicated portal has been created for the tracking of Investors and PPP projects in the state. | To achieve 100% accessibilty of the PPP regulation by Investors.
|  | (ii)To have a transparent and effective Public Private Partnership engagement process and procedures for efficient collaboration. | (ii) Develop a project pipeline and establish a transparent process for identifying and prioritizing projects suitable for PPPs. Templates for PPP contracts to streamline the negotiation process |  |  |  |  | 20th March, 2024 | 15th July, 2024 | Completed | The PPP project pipeline has been developed and published on the state official website. | Not Applicable
4 | Improved Investment Promotion Environment | (i) To create conditions that attract and retain investments in Ondo State | (i) Conduct a comprehensive review of existing regulations and streamline bureaucratic processes to reduce red tape | * To attracts domestic and foreign investment which would lead to increased capital inflows. This, in turn would stimulates * Fostering business expansion, job creation, and increased productivity. | * The State government *The Organized Private Sector * The Chambers of Commerce | Ondo State Development and Investment Promotion Agency (ONDIPA) | *Ministry of Commerce, Industry and Cooperatives *Performance and Project Implementation Monitoring Units (PPIMU) *Ministry of Finance *Ministry of Economic Planning and Budget. *Ministry of Justice | 10 April, 2024 | 30th Oct, 2024 | Completed Impact: Bureaucratic bottlenecks has been reduced by 60%. | Investment Process Map for the State has been developed and published on the Investment Promotion Agency website. | Not Applicable
|  |  | (ii)Develop strategy to enhance transparency in regulatory procedures and decision- making to build trust with investors. |  |  |  |  | 15 Jun, 2024 | 20th Sept, 2024 | Completed Impact: Same as (4i above) | Same as (4i above) | Same as (4i above)
|  |  | (iii)Frameworks to protect the rights of investors and ensure fair dispute resolution mechanisms. | [6 empty] | Completed Impact: 60% of Investment dispute between Investors and stakeholders has been amicably resolved. | ONDIPA has established a functional Griveance Redress Mechanism Unit to attend to, and resolve such complaints within 7 days. | Not Applicable
|  |  | (iv) ) Develop programs to assist investors with market research, business planning, and regulatory requirements. |  |  |  |  | 15th Feb, 2024 | 30th Nov, 2024 | Ongoing | The Ministry of Commerce and Industry is in consultation with the Chamber of Commerce and other Business related Association to develop a calendarized workplan for market research. | To ensure the completion of the workplan and publication of the regulatory requirement.
5 | Increase Transparency of official fees and procedures | (i) To be transparent and make public all fees, service delivery timeline and cost of all key business enabling environment state level MDAs. (ii)for Information sharing, grievances and redress mechanism within ODIRS on fees related issues. | (i)) Review the Ondo State Revenue Administration Law of 2018 to accommodate new fees and rates where and if necessary | (i)citizenry and public are aware of all government taxes and rate (ii)To ensure that all complaints are resolved within 72 hours; and where the complaint cannot be resolved within the 72 hours, the complainant must be notified of the efforts made to resolve the complaints. (iii) To blocked loopholes for revenue. | *The State Government *The citizenry * Business owners | Ondo State Internal Revenue Services | *Ministry of Environment *Ministry of Transport *Ondo State Signage and Advertisement Agency *Ministry of Lands *Ministry of Finance | 1st April, 2024 | 20th Jul., 2024 | Not yet Implemented | Not yet Implemented | Not Applicable
6 | Increase Transparency of fees and levies for inter exporters certification. | To regulate and promote interstate trades and other neigbouring State. | (i) Develop a dedicated, user-friendly,updated online portal providing detailed information on fees and levies applicable to inter-state trade. |  | *Government *Exporters *Business owner | Ministry of Commerce, industry and Planning and Budget | *Ministry of Finance *Ministry of Local Government and Chieftaincy Affairs.*NASSI | 1st Mar, 2024 | 30th Dec, 2024 | Completd. Impact: All fees and levies applicable to inter-state trade has been published on the ODIRS website. This has reduced the number of complaints on haulage, truck permit and touting activities on the state border post. | The Ministry of Commerce and Industry erected Bill Boards (10 numbers) across the state to sensitize the haulagers and trunk drivers on the applicable fee payeable on inter-state trade. | Our next step is to increase the Bill Board to 20 across the state.
|  |  | (ii) Establish a centralized certification system for exporters that streamlines the application and approval process | [6 empty] | Completed. Impact: The total number of exporters that have been issued certificate of export in the state by NEPC has increased from 20 in 2023 to 44 in 2024. | The State Government through the Ministry of Commerce and Industry in collaboration with NEPC has establish an exporters clausers with a view to indentifying potential exporters in the state; this has helped in the export certification program of the State Government. | Our next step is to expand the clauser so as to get more exporters certified.
|  |  | (iii) Develop programs to assist exporters with the certification process, including guidance on documentation and compliance | [6 empty] | Completed. Impact: The exporters are now aware of the need for certification, documentation, packaging and compliance to standard. | Three (3) sensitization program and seminar were held in year 2024 in collaboration with NEPC, Shippers' Council, SON, MAN and other City Chambers to further educate the exporters and would-be-exporters. | 3 more certification program to be organized in 2024.
7 | Simplified State and Local Tax regime | To reduce compliance burdens and attracting Investment | (i)Conduct a comprehensive review of existing state and local business tax laws and regulations. | (i)To remove illegal levies collectors on the borderlines of the State. | The State Government – Citizenry – Business owner/MSME | Ondo State Internal Revenue Services Ondo State Judiciary | *Ministry of Justice *Ministry of Finance *Ministry of Economic Planning and Budget |  |  | Not yet Implemented | Not Applicable | Not Applicable
8 | Quick Determination of Commercial Dispute | To establish a Special Court (e.g. Small Claims Court) for Commercial dispute of Micro and Small Enterprises. | (i) Constitute a five-man technical committee for the establishment of the Small Claim Courts. (ii) Conduct training for Magistrates and Registrars for the scheme (iii) Conduct awareness campaign to sensitize the public on the existence of the Small Claim Court. (iv) Employment of more Adjudicators such as Magistrates. | (i)To established at least (2) Small Claim Court in the State in year 2023 (ii) To maintain speedy and accelerated hearing | Medium and Small Scale Industrialist |  |  |  |  | No Activity | No Activity | No Activity
15th Mar 2024
30th Aug 2024.
2nd May, 2024
30th July, 2024
10th May, 2024
9th Oct, 2024
15th Aug, 2024
15th Dec, 2024
25 Jul, 2024
10th Dec, 2024
*Ministry of Commerce, Industry and Cooperative Services
1st Feb, 2024
20th Nov, 2024
25th Nov, 2024
10th Dec, 2024
5th Jan, 2024
15th Mar, 2024
30th June, 2024
20th April, 2024
5th Feb, 2024
16th July, 2024
8th Feb, 2024
19th Nov, 2024
20th Mar, 2024
5th July, 2024
11th July, 2024
20th July, 2024
The State Ministry of Lands and Housing have digitalized at least 70% of registered title documents.
This activity is a continuous project which will continue in year 2025, so as to achieve 100% digitalization of registered title documents.
On-going
Consultant has been engaged by the state Government to carry out the audit. The report of the audit exercise is yet to be submitted.
To follow up with the consultant to ensure timely completion of the audit exercise.
Not yet Implemented
Not yet Implemented
Not Applicable
Completed Impact: All loopholes for revenue diversion has been blocked.
The website of ODIRS contains all the list of revenue items, fees and rate.
ODIRS will Continue to maintain and regulary update the webiste.
Completed Impact: The time required for processing of licenses, approvals, permits etc. by the business enabling MDAs has reduced by 50% in each of the MDAs.
An Executive Order mandating the 5 business enabling MDAS to publish their procedure on the state official website has been signed by the Governor.
Not Applicable
Completed Impact: The problem of duplicity of taxes between the State Government and the Local Government has been eradicated as a result of the single demand notice for tax collection.
ODIRS has executed an agreement with each of the Local Government to collect all the Local Government taxes on thier behalf and remite the agreed percentage of revenue collected to the Local Government
Ongoing
Not Applicable
The draft of the law has been forwarded to the Ministry of Justice for their input
Follow up with the Ministry of Justice to get the final copy of the draft law and forward same to the House of Assembly for neccessary action.
(iii) Commence the process of passing a new law to adopt Presumptive Turnover Tax Regime for MSME
(ii) Harmonize certification standards making it easier for multiple requirements.
(v) Conduct regular audits registration system to issues of the property identify and address any promptly.
(iii) Develop model agreements that streamline the process of forming partnerships and address risk-sharing mechanism.
(ii) Ensure that the Revenue contains all approved rates and fees is published and maintained on the Ondo State Government website as well as the website of the Ondo State Internal Revenue Services and key business enabling MDAs.
(iii)Publish the procedures and timeline for service delivery for 5 key business enabling MDAs (Business Premises Permit by Ministry of Commerce and Industry, EIA by Ministry of Environment, Signage permit Inspection Certificate by Ministry of Transport and Survey Plan by Ministry of Lands.
(iv) Continue with public awareness program on TV, Radio andother new media on the available electronic platform for payment of all government revenue.
(ii)Consolidate various tax codes and regulations into a single, comprehensive tax code
15th Jan, 2024
15th Aug, 2024